## Product Backlog
Restaurent App | User Story Map[Product BackLog]
| Release-1 | Epic | Epic | Epic | Epic
|  | Browse | Order | Pay | Track
|  | User Story | User Story | User Story | User Story
|  | Group by Categories | Registration | Cash | ETA
|  | Serach By keyword | Login | Debit/Credit Card | Support
Add & Remove from Cart
| Release -2 |  |  | InternetBanking | Order Progress
| Release-3 |  | Previous Order/ReOrder | Payment Wallets | Live Tracking

## Sprint BackLog
User Story Map[Product BackLog] |  |  |  |  | User Story Map[Sprint BackLog with Story Points]
Release-1 | Epic | Epic | Epic | Epic | Release-1 | Epic |  | Epic |  | Epic |  | Epic
| Browse | Order | Pay | Track |  | Browse |  | Order |  | Pay |  | Track
| User Story | User Story | User Story | User Story |  | User Story | Story Points | User Story | Story Points | User Story | Story Points | User Story
| Group by Categories | Registration | Cash | ETA |  | Group by Categories | 20 | Registration | 40 | Cash | 10
| Serach By keyword | Login | Debit/Credit Card | Support |  | Serach By keyword | 30 | Login | 20 | Debit/Credit Card |  | Support
|  | Add & Remove from Cart | [5 empty] | Add & Remove from Cart | 70
Release -2 |  |  | InternetBanking | Order Progress | Release -2 |  |  |  |  | InternetBanking |  | Order Progress
Release-3 |  | Previous Order/ReOrder | Payment Wallets | Live Tracking | Release-3 |  |  | Previous Order/ReOrder |  | Payment Wallets |  | Live Tracking
User Story Map[Sprint BackLog with Sprint]
[5 empty] | Release-1 | Sprint-1
[6 empty] | User Story | Story Points
[6 empty] | Serach By keyword | 30
[6 empty] | Registration | 40
[6 empty] | Login | 20
[6 empty] | Cash | 10
[6 empty] | Total[Maximum Estimate Allowed] | 100
User Story Map[Sprint BackLog with Sprint]
[5 empty] | Release-1 | Sprint-2
[6 empty] | User Story | Story Points
30
40
10
20
[6 empty] | Total[Maximum Estimate Allowed] | 100

## Events&Ceremonies
E
Events/Ceremonies in Agile Methodolgy(SCRUM)
| 1 | 2 | 3 | 4
| Sprint Planning | Daily Scrum | Sprint Review | Sprint Retrospective
| To Craft a Sprint Goal and aplan to achieve it | To Review Teams Progress on Sprint goals and adjust the plan to get there | To the review the work completed in the sprint with stake holders | To Review the product development and process and identify the areas for continuous improvements